## Sheet1
Time (UTC) | Event | Actions Taken
02:00 PM | High traffic volume detected on web servers. | Initial anomaly detected but not yet classified.
02:05 PM | Network monitoring tools trigger an alert for unusual traffic spikes. | SIEM logs analyzed for threat patterns.
02:10 PM | SOC analysts review logs and confirm potential DDoS attack. | SOC determines traffic originates from multiple botnets.
02:15 PM | Firewall and Intrusion Prevention System (IPS) begin filtering traffic. | Rate-limiting and geo-blocking applied to reduce attack impact.
02:30 PM | Attack escalates, impacting customer-facing applications. | Customer support team notified of service disruption.
02:45 PM | Incident Response team activates DDoS mitigation plan. | SOC coordinates with ISP and cloud service providers for mitigation.
03:00 PM | Traffic is redirected through Cloud-based DDoS protection services. | Traffic scrubbed through CDN-based protection.
03:15 PM | Network engineers identify attack sources and update firewall rules. | IP blacklists updated to prevent further traffic from malicious sources.
03:45 PM | Partial recovery of web services achieved. | Critical services restored with some latency.
04:00 PM | Full network stabilization achieved, but logs indicate a secondary attack attempt. | SOC enhances threat intelligence monitoring for further attack attempts.
04:30 PM | Forensic analysis of attack vectors begins. | Post-incident forensic analysis conducted to assess vulnerabilities.
05:00 PM | Incident report completed, and post-incident review initiated. | Key learnings documented for future DDoS mitigation strategies.